## Renewal Execution Plan
Renewal Plan prepared for <Name>
Dated Prepared/Presented/Updated: 02/27/19
Enterprise Agreement Renewal Execution Plan
Timeline & Target Details
| ON TIME RENEWAL DATE | EARLY RENEWAL DATE | MILESTONE | POSITION | BASELINE | Position Adjusted | Date adjusted | Milestone adjusted | DESCRIPTION
Monday | 2019-02-25 | 2018-11-27 | Planning Kick-Off / Business Technology Review | 17 | 0 | Planning Kick-Off / Business Technology Review | 2019-02-25 | 43431 | Q1 Quarterly CVP Meeting
Monday | 2019-02-25 | 2018-11-27 | Review Initial Renewal Analysis | -10 | 0 | Review Initial Renewal Analysis | 2019-02-25 | 43431 | Q1 Quarterly CVP Meeting
Monday | 2019-03-18 | 2018-12-18 | Begin Licensing TechCheck Assessment | 5 | 0 | Begin Licensing TechCheck Assessment | 2019-03-18 | 43452 | Kickoff Meeting with Assessment Team
Monday | 2019-04-15 | 2019-01-15 | Develop Product Evaluation Plan | 15 | 0 | Develop Product Evaluation Plan | 2019-04-15 | 43480 | Value Discovery Workshop
Monday | 2019-05-06 | 2019-02-05 | Microsoft Product Roadmap Discussion | -13 | 0 | Microsoft Product Roadmap Discussion | 2019-05-06 | 43501 | Microsoft Technology Center/Customer Immersion Experience
Monday | 2019-06-03 | 2019-03-05 | Finalize Licensing TechCheck | 18 | 0 | Finalize Licensing TechCheck | 2019-06-03 | 43529 | Sign-off on TechCheck Results
Monday | 2019-06-24 | 2019-03-26 | Begin Final True-up Analysis | -7 | 0 | Begin Final True-up Analysis | 2019-06-24 | 43550 | Q2 Quarterly CVP Meeting
Monday | 2019-07-01 | 2019-04-02 | Start Contract Legal Review | 10 | 0 | Start Contract Legal Review | 2019-07-01 | 43557 | Send out blank contracts for Legal Review
Monday | 2019-07-15 | 2019-04-16 | Finalize Product Selection for Renewal | -12 | 0 | Finalize Product Selection for Renewal | 2019-07-15 | 43557 | Prepare Preliminary Customer Price Sheet (CPS)
Tueday | 2019-07-30 | 2019-05-01 | Review Final Renewal Quotes | 18 | 0 | Review Final Renewal Quotes | 2019-07-30 | 43557 | Review Microsoft's Official Proposal
Monday | 2019-08-05 | 2019-05-07 | Submit Final True-Up | -6 | 0 | Submit Final True-Up | 2019-08-05 | 43586 | Submit Final True-up and Reconcile Online Reservations
Thurday | 2019-08-15 | 2019-05-17 | Final CPS & Contract Creation | 8 | 0 | Final CPS & Contract Creation | 2019-08-15 | 43592 | Finalize Negotiation with Microsoft and Create Contract
Tuesday | 2019-08-20 | 2019-05-22 | Execution of EA Contract | -18 | 0 | Execution of EA Contract | 2019-08-20 | 43602 | Sign-off on Official Contract
Formulas:
ON TIME RENEWAL DATE = [ON TIME RENEWAL DATE, row below]
ON TIME RENEWAL DATE = SUM([ON TIME RENEWAL DATE, row below]-21)
EARLY RENEWAL DATE = SUM([ON TIME RENEWAL DATE]-90)

## Project Data Sorted (hidden)
Sort the dates to populate the timeline in chronological order
|  |  | data analysis | [5 empty] | Actual data to chart, which is fed into the Project Timeline worksheet via hidden columns F-H.
| start row | 9 | TIE BREAK | RANK | DATE | MILESTONE | POSITION | NUM | RANK Sorted | DATE | MILESTONE | POSITION
| last entry | 21 | 13 | 1 | 2019-02-25 | 43431 | Planning Kick-Off / Business Technology Review | 12 | 13 | 2019-02-25 | 43431 | Planning Kick-Off / Business Technology Review
|  |  | 12 | 2 | 2019-02-25 | 43431 | Review Initial Renewal Analysis | 11 | 12 | 2019-02-25 | 43431 | Review Initial Renewal Analysis
|  |  | 11 | 3 | 2019-03-18 | 43452 | Begin Licensing TechCheck Assessment | 10 | 11 | 2019-03-18 | 43452 | Begin Licensing TechCheck Assessment
|  |  | 10 | 4 | 2019-04-15 | 43480 | Develop Product Evaluation Plan | 9 | 10 | 2019-04-15 | 43480 | Develop Product Evaluation Plan
|  |  | 9 | 5 | 2019-05-06 | 43501 | Microsoft Product Roadmap Discussion | 8 | 9 | 2019-05-06 | 43501 | Microsoft Product Roadmap Discussion
|  |  | 8 | 6 | 2019-06-03 | 43529 | Finalize Licensing TechCheck | 7 | 8 | 2019-06-03 | 43529 | Finalize Licensing TechCheck
|  |  | 7 | 7 | 2019-06-24 | 43550 | Begin Final True-up Analysis | 6 | 7 | 2019-06-24 | 43550 | Begin Final True-up Analysis
|  |  | 6 | 8 | 2019-07-01 | 43557 | Start Contract Legal Review | 5 | 6 | 2019-07-01 | 43557 | Start Contract Legal Review
|  |  | 5 | 9 | 2019-07-15 | 43571 | Finalize Product Selection for Renewal | 4 | 5 | 2019-07-15 | 43571 | Finalize Product Selection for Renewal
|  |  | 4 | 10 | 2019-07-30 | 43586 | Review Final Renewal Quotes | 3 | 4 | 2019-07-30 | 43586 | Review Final Renewal Quotes
|  |  | 3 | 11 | 2019-08-05 | 43592 | Submit Final True-Up | 2 | 3 | 2019-08-05 | 43592 | Submit Final True-Up
|  |  | 2 | 12 | 2019-08-15 | 43602 | Final CPS & Contract Creation | 1 | 2 | 2019-08-15 | 43602 | Final CPS & Contract Creation
|  |  | 1 | 13 | 2019-08-20 | 43607 | Execution of EA Contract | 0 | 1 | 2019-08-20 | 43607 | Execution of EA Contract